# CCIP Bridging Project Work Plan

CCIP-BR-13 Fine Scale Modelling

1	Project Summary

### 1.1   Project full title

Integrative fine-scale habitat suitability and metapopulation modelling for targeted Crown-of-Thorns Starfish management

### 1.2	Project summary

Provide a summary of the project. (50 words maximum)

To improve operational efficiency and standardise surveillance by developing fine-scale predictive habitat suitability models for Crown-of-Thorns Starfish (COTS), and by prototyping a fine-scale metapopulation model underpinned by new sub-scale connectivity networks. Leveraging fine-scale observation, habitat and connectivity data, these models will allow critical management decisions to be explored at an operational (i.e., sub-reef) scale.

### 1.3 Nominated Personnel

List all personnel who will be involved and their role in project delivery (e.g. lead, co-investigator, research assistant). Add additional rows if necessary. Use ‘TBD’ for name if personnel is still to be recruited.

| Name | Organisation | Project role & expertise |
| --- | --- | --- |
| Samuel Matthews | AIMS | Project lead; COTS decision support expert; developer of COTS Control Dashboards |
| Dr. Takuya Iwanaga | AIMS | Decision scientist; expert in scalable, robust ecosystem modelling and sensitivity analysis |
| Prof Mike Bode | QUT | Population modeller; expert in spatial ecological modelling and conservation planning |
| Owen Stewart | QUT | Reef-scale modeller; contributes to integration and validation of modelling frameworks |
| Dr. Severine Choukroun | JCU | Connectivity modeller; leads development of fine-scale larval dispersal networks |
| Bridget Beesley | AIMS | GIS and spatial data specialist; prepares high-quality maps for field and operational use |
| Jennifer Wilmes / Isobel Ryan | GBRMPA | Stakeholder liaison and operational integration support for GBRMPA |

Summarise how the team will work together to deliver the project. Highlight any cross-disciplinary or multi-institutional collaborations.

The project team comprises a cross-disciplinary group of experts spanning multiple leading institutions (AIMS, QUT, JCU, GBRMPA), each with a proven track record in delivering high-impact ecological modelling and decision-support projects relevant to Crown-of-Thorns Starfish (COTS) management. Samuel Matthews (AIMS), as Project Lead, brings over eight years of experience leading the design, development, and delivery of the GBR COTS Control Dashboards, currently the core operational decision-support system used by managers and contractors across the Marine Park. His unique insight into real-world operational needs ensures the project is tightly aligned with management priorities and feasible within existing workflows. Dr. Takuya Iwanaga (AIMS) contributes advanced expertise in scalable, robust, and efficient ecosystem modelling. He has successfully delivered complex model implementations within ADRIA, CoralBlox and C-scape and integrations with ReefMod, and is responsible for ensuring methodological rigor and computational efficiency. Professor Mike Bode and Owen Stewart (QUT) are leaders in reef-scale and spatial ecological modelling, particularly with respect to COTS. Their involvement ensures conceptual alignment with ongoing modelling initiatives and enables integration of outputs into broader regional frameworks. Moreover, Mike Bode is a thought leader in conservation management ensuring our approaches align with best practice and emerging trends. Their involvement fosters coordination across programs and strengthens the project’s scientific foundation. Dr. Severine Choukroun (JCU) is a leading expert in hydrodynamic and larval connectivity modelling for the GBR and is responsible for generating fine-scale larval dispersal networks tailored for COTS biology. These networks underpin the metapopulation modelling component. Bridget Beesley (AIMS) provides critical GIS and spatial analysis expertise, ensuring high-quality outputs are operationalised through mapping platforms such as the GBRMPA ESRI Field Maps app. Jennifer Wilmes and Isobel Ryan (GBRMPA) provide strategic and analytical input and ensure alignment with reef management planning processes and analytical tools (Dashboards), enhancing the likelihood of uptake and real-world application of project outcomes. This multidisciplinary, multi-institutional collaboration ensures successful delivery and long-term impact.

2	Objectives and Activities

### 2.1 	Objectives

Tick the priority research area(s) this project supports

| Tick if applies | Priority research area | Details |
| --- | --- | --- |
|  | Detection & Monitoring | Research that advances development and operational deployment of tools and strategies that improve COTS, coral and co-benefit monitoring capabilities. |
| ☐ | Innovating Control Methods | Research that advances development of an expanded control toolbox to complement culling and/or address its limitations (e.g. depth, COTS life-history stage). |
| ☐ | COTS, Coral & Climate Change | Research that generates new knowledge and improved capability to adapt COTS management to changing environmental conditions. |
|  | Decisions for Coral Resilience | Research that advances development and application of models and decision support tools that guide COTS Control Program strategic planning and tactical operations. |

Explain the rationale for this project and how it addresses at least one of the priority research areas (Section 2.1). List the project’s specific objectives as bullet points. If the project builds on research previously funded through CCIP, explain how this project advances knowledge and capability from previous investments.

Many critical COTS management decisions are made at the sub-reef scale on an ad-hoc basis. Current metapopulation models cannot support this context as they operate at coarser reef scales, lack direct COTS components, or are insufficiently spatially explicit. This project will couple habitat suitability modelling, fine scale connectivity modelling, and sub-reef meta-population modelling for the purpose of holistic operational decision support. Outcomes include standardised surveillance paths and computational tools to explore management decision implications. This work advances CCIP’s "Decisions for Coral Resilience" priority by bridging detailed habitat mapping, connectivity modelling, and COTS management. It provides foundational capability towards CCIP 2.0 goals of improving fine-scale modelling capability to increase tactical and strategic efficiencies. Activities will leverage recent (and ongoing) advancements from AIMS, RRAP, and the Pilot Deployment Program. Extending these to COTS management will enable improved suitability predictions and help refine surveillance and outbreak detection efficiency, thereby also advancing the “Detection and Monitoring” priority. Methodological improvements around the modelling will be made with a view to apply the innovations in other relevant modelling architectures (e.g., ReefMod, ADRIA, CoralBlox, C~scape). Specific objectives include: - Development of GBR-wide predictive fine-scale habitat suitability models by connecting fine scale COTS abundance data to newly developed high-resolution benthic and coral habitat data. - Optimise and standardise surveillance paths to improve outbreak detection and operational efficiency, including a comparative assessment against traditional perimeter-based surveillance. - Refined management strategies for distinct reef habitat types as determined through predicted suitable habitats and metapopulation modelling

### 2.2 	Activities and methods

Describe the activities that will be undertaken to achieve the project objectives. Include information on the methods, tools and experimental / sampling design (as applicable) and explain the novelty and innovation of the proposed approach.

- Predictive Habitat Suitability Modelling: High-resolution coral habitat data from ongoing work at AIMS will be combined with location specific COTS data (SALAD, ReefScan Deep, RHIS, culling) for fine scale habitat suitability modelling. We will employ machine learning techniques to predict COTS habitat suitability at spatial resolutions of approximately 30-100m for the entire GBR, refining the accuracy of operational surveillance and reducing survey areas significantly. We will validate simulated manta tow paths at the 50th and 80th percentile thresholds against historical COTS outbreak data, quantifying both operational improvements in terms of survey time and effort and probabilities of detecting all outbreak levels (i.e. “Non Outbreak”, “Potential”, “Established”, “Severe”). - Fine-scale Connectivity Modelling: This component involves generating fine-scale connectivity networks specifically tailored to COTS biology. Leveraging existing RRAP and PDP-funded hydrodynamic models and computational grids, we will adapt these resources to represent larval dispersal accurately at cluster scales relevant to COTS management (Lizard, Moore, Davies, Heron). These networks will serve as critical inputs to both the predictive habitat suitability and metapopulation models. - Prototype Fine-scale Metapopulation Modelling: We will create a computationally efficient fine-scale metapopulation model using approaches developed in existing AIMS coral models CoralBlox and C~scape. This project will deliver a working prototype metapopulation model at a single, data-rich reef cluster (e.g., Lizard Island) to test feasibility and value of fine-scale, COTS control modelling, building on the newly developed fine-scale connectivity modelling. Regional-scale larval supply inputs (e.g., outbreak phase simulations) from GBR-wide hindcasts of COTS populations will be used as boundary conditions to drive fine-scale dynamics within test clusters. This nested approach will be combined with scenario exploration across multiple “modes” of larval supply to ensure biological realism and allow for advanced scenario testing capabilities. The model will be validated using detailed, site-specific data from selected reef clusters (SALAD, Culling), to assess whether the model can reproduce past outbreak and recovery trajectories at key reef clusters. Model outcomes will provide unprecedented insights into within- and between-reef population dynamics and their implications, greatly enhancing strategic decision-making capabilities. - Operational Evaluation and Management Implications: Using the developed metapopulation model, we will have the foundation to undertake detailed scenario analyses addressing critical management decisions, specifically exploring the effectiveness of continuing versus discontinuing control efforts in high-density COTS outbreak scenarios (the "stopping rule")). The development of this capability will bridge to future projects and allow us to simulate various management scenarios at the cluster scale, generating recommendations and strategic insights directly applicable to currently unresolved operational management concerns. - Stakeholder Engagement and Feedback: We will ensure the operational relevance and uptake of modelling outputs through structured stakeholder engagement. Operational workshops involving reef managers, control teams, and Traditional Owners will be held during GBRMPA’s established November Pre-Spawning and April Prioritisation workshops. Additionally, the project's habitat suitability and connectivity outputs can be integrated into GBRMPA’s ESRI Field Maps app, enabling continuous feedback and engagement. This approach will also facilitate meaningful comparison with Traditional Owner knowledge (through engagement with TO owned and operated COTS control vessels) and practical operational insights. - Novelty and Innovation: This project offers significant methodological innovations by integrating multiple cutting-edge tools and models into an operational context. The explicit inclusion of fine-scale hydrodynamic connectivity tailored specifically to COTS biology is novel and addresses a critical management gap. Additionally, translating complex ecological models into practical, decision-ready tools and interactive spatial layers (fine scale habitat suitability) ensures direct applicability and adoption by management teams. Collectively, this project represents a substantial advancement in developing more targeted and effective COTS management on the GBR.

3 	Outputs and Impact Pathway

### 3.1     Outputs

Provide a list of outputs which will be delivered as a result of the project (excluding the internal reports and financial acquittal). These outputs could be new knowledge, tools, technologies, data, documents (e.g. SOPs, plans), publications. Add rows as required.

| ID | Outputs | Due date |
| --- | --- | --- |
| A | Traditional Owner information package and documentation for TO operators | 15 April 2025 |
| E | Finalised GBR-wide Habitat Suitability Model and surveillance paths | 30 June 2026 |
| F | Finalised and validated fine scale connectivity network at four reef clusters | 30 June 20206 |
| G | Prototype of a fine-scale metacommunity model calibrated and validated at one reef cluster, including sensitivity analysis and preliminary scenario testing for a single reef cluster | 31 August 2026 |
| H | Final project data sets and final report are made publicly available, meeting FAIR data standards. | 6 November 2026 |
| I | Peer review publications of Fine Scale Suitability Model |  |

### 3.2	Outcomes and impact pathway

Tick the outcome(s) the project will deliver on in support of the CCIP vision that “the health and resilience of the Great Barrier Reef and its connected people and industries are protected from the impacts of COTS outbreaks’’.

| Tick if applies | Outcome for COTS Management |  |
| --- | --- | --- |
| ☐ | 1 | A step-change in detection and monitoring supports COTS management planning, operations and evaluations |
|  | 2 | Response to COTS outbreaks is highly effective, efficient, scalable and innovative to keep pace with climate change |
| ☐ | 3 | Traditional Owners, industry and community are integrated into COTS research and management |
|  | 4 | COTS management decision-making is informed by cutting-edge biophysical, social and predictive knowledge |

Describe the outcomes and benefits that will be generated through this project. What will change because of the project? What is its pathway to achieving impact? (300 words maximum)

This project delivers critical advances across multiple dimensions of Crown-of-Thorns Starfish (COTS) management. By integrating high-resolution SALAD data, ReefScan Deep imagery, and fine-scale connectivity models, it will significantly enhance surveillance efficiency, precision, and standardisation. This GBR-wide predictive habitat suitability approach will reduce the time and resources spent surveying low-probability areas, enabling earlier detection and faster, targeted intervention. Fine-scale connectivity networks will be explicitly adapted to COTS biology, offering essential insight into larval dispersal at previously unresolved spatial scales for key clusters on the GBR. These outputs will inform habitat and metapopulation models, enabling targeted control at localised source and sink locations within reef clusters, improving outbreak suppression. If built upon in CCIP 2.0, this could markedly improve program effectiveness. The proposed fine-scale metapopulation model represents a major step forward, enabling the evaluation of complex and unresolved management trade-offs—such as when to cease (“stopping rules”) or initiate (“starting rules”) control efforts on heavily affected reefs. This capability will improve both tactical decisions and longer-term strategies such as primary outbreak suppression. Successful prototype development will inform future application in established models such as C-scape, CoralBlox, and ADRIA. Impact Pathway: Immediate impacts include operational gains for GBRMPA and contractors, with direct cost savings and improved coral protection. Medium-term benefits stem from integration into prioritisation process and the Integrated Pest Management (IPM) frameworks—for instance, by incorporating suitable habitat area metrics (combined with workability) and reducing survey footprints to maintain reef closure status. Longer-term, the combination of fine-scale habitat, connectivity, and metapopulation modelling has the potential to transform how we prioritise and deploy control by focusing on the most influential sub-reef habitats. Strong existing partnerships, delivery experience, and stakeholder engagement via workshops and operational platforms will maximise uptake and real-world impact. Feasibility of scale-up (incl. data-poor locations). While the predictive habitat maps are GBR wide, the metapopulation model is designed to test management scenarios across a representative sample of data-rich clusters, generating simple, transferable rules that can guide control in less well-studied areas. Future extensions could apply the framework to more reef cluster with basic connectivity data and minimal survey inputs.

Describe any complementarity or overlap between this and other projects/ research funded through CCIP or other programs, especially the Reef Restoration and Adaptation Program (RRAP) or the National Environmental Science Program (NESP). Where relevant, describe how this project will be managed to promote greater cross-program coordination. (200 words maximum)

This project strongly complements, and strategically leverages, ongoing research funded by the National Environmental Science Program (NESP) and the Reef Restoration and Adaptation Program (RRAP). Specifically, fine-scale coral habitat data collected under NESP’s SALAD project forms an essential foundation for our predictive habitat suitability modelling component. Additionally, our connectivity and metapopulation modelling significantly benefit from RRAP-funded fine-scale connectivity research, allowing efficient adaptation and extension to Crown-of-Thorns Starfish biology without duplicating existing efforts. To maximise coordination and avoid overlap, regular communication has already been established with SALAD principal investigators (Prof. Morgan Pratchett), RRAP connectivity modellers, and the broader ReefScan team. Ongoing coordination will be facilitated through joint workshops and structured meetings within GBRMPA’s existing management forums, enabling clear delineation of research outputs, data sharing, and model integration pathways. Additionally, we will coordinate closely with GBRF as funders and GBRMPA as end-users, ensuring alignment with broader program objectives and management strategies. This approach not only prevents redundancy but actively promotes synergistic outcomes, enhanced resource utilisation, and broader integration of innovative methodologies across key reef management initiatives.

4	Project Management

### 4.1 Stakeholder Engagement

Who will benefit from the project’s outcomes and how will they be engaged during the project? These stakeholders could be other researchers, reef managers, control crews, tourism operators, etc.

Primary beneficiaries of this project include reef managers, operational COTS control teams, Traditional Owners, and researchers. Reef managers and GBRMPA operational teams will directly benefit from improved efficiency, reduced operational costs, and clearer strategic guidance enabled by the predictive habitat suitability models, connectivity networks, and metapopulation scenario analyses. Operational control crews, including Traditional Owner-operated businesses Malu Ventures and Jabalbina, will benefit through enhanced targeting and reduced surveillance effort, significantly improving day-to-day field operations. Extensive consultation has shaped this proposal. Detailed discussions were held with senior managers and quality assurance officers at GBRMPA to ensure operational relevance and utility. Alignment with funding priorities and broader strategic objectives was confirmed through engagement with the Great Barrier Reef Foundation (GBRF). Further, consultations with leading researchers in the COTS management space, including Prof. Morgan Pratchett (SALAD), Sven Uthicke (eDNA monitoring), and the ReefScan Deep team, ensured methodological alignment and complementarity across related research initiatives. Discussions with RRAP connectivity modellers also verified the value and feasibility of integrating their existing fine-scale connectivity efforts with this project's objectives. This extensive stakeholder engagement ensures broad support, alignment, and maximised impact of project outcomes.

### 4.2 Traditional Owner Opportunities

Provide a description of Traditional Owner and First Nations Peoples engagement and opportunities that will form part of this project. Include how the project team will engage with Traditional Owners including what communications/ deliverables are appropriate and how these will be resourced.

This project will not involve new fieldwork or collection of samples from Sea Country. Instead, it leverages extensive existing datasets, including data collected under previous projects and operational COTS management programs. The project team has established relationships with key Traditional Owner groups involved in COTS control, specifically Malu Ventures (Torres Strait) and Jabalbina (Eastern Kuku Yalanjiwarra Country). Prior engagement has occurred through regular participation in GBRMPA-led management workshops and ongoing discussions around enhancing operational efficiency, aligning scientific research outputs with Traditional Owner priorities and practical management needs. There are clear opportunities for Traditional Owners to benefit directly from this research through targeted communication, knowledge exchange, and operational collaboration. Given the nature of this research—producing fine-scale habitat suitability maps, connectivity hotspots, and metapopulation modelling outcomes—there is significant potential to support Traditional Owner-led COTS management and broader Sea Country management objectives. Appropriate engagement activities will include: - On-Country visits with Malu Ventures and Jabalbina to discuss and interpret model outputs, specifically habitat suitability maps and connectivity hotspots, ensuring alignment with Traditional Owner knowledge and practices. - Tailored information sheets and visual outputs summarizing key findings and their relevance to local management practices, enabling Traditional Owners to apply research insights directly to their operational activities. - Presentation and interactive discussion of project results during existing GBRMPA bi-annual planning workshops (Pre-Spawning and Prioritisation workshops) and regular COTS Operations Group meetings, where Traditional Owners actively participate. - Incorporating Traditional Owner perspectives and feedback into model refinement, ensuring outputs remain culturally relevant and operationally practical. These structured engagements are an opportunity to ensure Traditional Owner groups actively participate in interpreting and applying research outcomes, thus enhancing local operational efficiencies and supporting broader capacity building within their respective COTS management teams To support meaningful engagement, we have nominally budgeted $4,000 to facilitate a knowledge-sharing visit to either Malu Ventures (Torres Strait) or Jabalbina (Eastern Kuku Yalanjiwarra Country), depending on logistical feasibility and interest. This funding will cover travel, accommodation, and workshop materials to enable on-Country discussions of model outputs (e.g. habitat suitability and connectivity maps) and their alignment with Traditional Owner priorities. In addition, we will leverage existing GBRMPA-led engagement platforms, including the bi-annual Pre-Spawning and Prioritisation workshops and COTS Operations Group meetings, where Traditional Owner representatives are routinely brought together. Participation in these forums allows efficient communication of project outcomes, collection of feedback, and integration of Traditional Owner perspectives without incurring significant additional costs. These resourcing approaches ensure Traditional Owner involvement is feasible, cost-effective, and integrated into existing coordination mechanisms, maximising opportunities for two-way knowledge exchange and operational impact.

### 4.3	Risk identification and management

Identify the key risks that could impact the ability of the project to achieve its objectives and deliver its intended outcomes. How will the project team manage these risks? Review and update the pre-tabulated risks to make them project specific. Add risks/ rows as needed.

| Risk type | Risk description | Mitigation strategy | Risk owner |
| --- | --- | --- | --- |
| Technical Risk | Delays in delivery of fine-scale connectivity outputs from linked RRAP projects | Maintain close coordination with JCU/CSIRO team; ensure contingency timelines in modelling tasks; prioritise clusters with existing data | Dr. Severine Choukroun |
| Scope / Delivery Risk | Scope creep or underestimation of time required to deliver multiple model components | Refine deliverables to focus on prototype development for one or two key reef clusters; clearly stage future expansion in follow-up proposals | Sam Matthews (Project Lead) |
| Data Dependency Risk | SALAD or ReefScan Deep data are incomplete, delayed or unavailable for chosen clusters | Leverage existing high-quality sites; coordinate early with NESP/REEFScan teams to secure access and clarify intended use | Sam Matthews |
| Integration Risk | Difficulty integrating outputs into operational tools (e.g. GBRMPA Field Maps, Dashboards or prioritisation frameworks) | Engage with GBRMPA dashboard and GIS leads from early stages; ensure alignment with platform requirements and regular review through workshops | Jennifer Wilmes / Isobel Ryan |
| Stakeholder Engagement | Limited feedback or engagement from Traditional Owners or contractors due to timing or operational constraints | Align communications with existing workshops and COTS Ops Group meetings; use established relationships for targeted, meaningful engagement | Sam Matthews |
| Reputational Risk | Miscommunication or misinterpretation of model outputs or limitations by stakeholders | Provide clear documentation of model assumptions, limits and intended uses; facilitate interpretation through workshops and visual aids | Sam Matthews / Takuya Iwanaga |
| Staff Capacity Risk | Key personnel availability (e.g. illness, competing demands) impacts ability to deliver | Distribute responsibilities across team; allocate sufficient time and use flexible capacity within AIMS and partner teams | Sam Matthews / Takuya Iwanaga |

5   Budget

### 5.1 Budget summary

Summarise the overall project budget based on the detail provided in the CCIP budgeting tool. All figures to be AUD and excluding GST.

| Cost Category | Total Requested | Total co-contribution |
| --- | --- | --- |
| Personnel Salaries | $136,422 | $76,225 |
| Facilities | - | - |
| Fieldwork | $4,000 | - |
| Project management | $9,000 | - |
| Consumables / equipment | - | - |
| Contractors / consultants | - | - |
| TOTAL (AUD), excl. GST | $149,422 | $76,225 |

### 5.2  Budget details

Provide a rationale for the personnel allocation budgeted for the project including any variations from the rates in the CCIP budgeting tool.

The personnel budget reflects targeted allocations across modelling, stakeholder engagement, and integration tasks central to project success. Personnel costs cover partial time allocations for senior scientists and modelling experts (AIMS, QUT, JCU), aligned with their defined project roles. The rate assumptions are based on standard AIMS salary bands and CCIP guidelines, unless noted. The co-contribution reflects significant in-kind support from project participants, particularly AIMS staff, enabling project delivery at lower direct cost to the funder. This co-investment ensures delivery of high-impact outputs, including predictive SDMs and prototype metapopulation models, at minimal public funding.

Provide a rationale for the operational expenses budgeted for the project (e.g. facilities, fieldwork, project management, travel, engagement, consumables and equipment).

- Fieldwork ($4,000): Budgeted for Traditional Owner engagement trips (e.g. Malu Ventures, Jabalbina) to share and discuss model outputs (habitat maps, connectivity layers), enabling two-way learning and supporting Sea Country management. - Project Management ($8,000 requested, $1,500 co-contribution): Covers reporting, coordination across multi-institutional teams, and integration with GBRMPA stakeholder processes. Co-contribution from AIMS reflects internal management time and in-kind administrative support. - Facilities, Consumables, Contractors: No funds are requested for these categories. The project strategically leverages existing computational infrastructure, datasets, modelling tools (e.g. CoralBlox, C-SCAPE), and engagement platforms (e.g. Field Maps, COTS Operational Group meetings).

6	Monitoring and reporting

### 6.1 Deliverables

List and describe the milestones and deliverables (i.e. outputs) that will be produced to achieve the project’s objectives, and their due dates. Required planning and reporting deliverables are pre-filled. Add/remove rows as required.

Note that all project activities must be completed by 15 October 2026 with final reporting completed by 6 November 2026.

| ID | Milestones & Deliverables | Description | Due date |
| --- | --- | --- | --- |
| 1 | Traditional Owner Communications and Engagement Plan | Provide a brief outline of the purpose and plans for communications and engagement and the intended outcomes. Template provided. | 15 November 2025 |
| 2 | Initial meetings with TO Groups | Meeting during November COTS workshop to develop plan for integration of outputs | TBA November/December |
| 2 | Prototype workflow for Habitat Suitability Model | Establish an initial computational workflow for predictive habitat suitability modelling | 15 Dec 2025 |
| 3 | Initial fine scale connectivity networks | Develop preliminary fine-scale connectivity networks for critical reef clusters | 15 January 2026 |
| 4 | Workshop with GBRMPA | Engagement to refine methods, gather feedback, and discuss practical application scenarios with GBRMPA stakeholders | 30 January 2026 |
| 5 | Progress Report | Provide a progress report (internal) on project delivery. Template provided. | 6 February 2026 |
| 6 | Prototype Metacommunity model framework | Develop and document the initial fine-scale metacommunity model framework for a single reef cluster | 28 February 2026 |
| 7 | On-country trips to socialise outputs | Trips to Jabalbina (Mossman) and Malu Ventures (TI) to showscase outputs and field test | April-May 2026 |
| 8 | Finalised Habitat Suitability Model and surveillance paths | Complete and validate predictive habitat suitability model and operational manta tow surveillance paths | 30 June 2026 |
| 9 | Finalised and validated fine scale connectivity network | Fully develop and validate fine-scale connectivity models for all critical reef clusters | 30 June 2026 |
| 10 | Workshop with GBRMPA | Identify all potential use cases for refined modelling approaches, integration pathways, and stakeholder feedback on operational adoption | 31 July 2026 |
| 11 | Calibrated metacommunity model | Calibrated and validated prototype of fine-scale metacommunity model, including sensitivity analysis and preliminary scenario testing for a single reef cluster | 31 August 2026 |
| 12 | Final Reports and datasets | Final Report (internal). Provide a report on project delivery. Template provided. Final Report (public). Provide a brief report to communicate key findings, outcomes and recommendations to stakeholders. Template provided. Final project data sets are made publicly available, meeting FAIR data standards. | 6 November 2026 |
|  | Financial acquittal | Final financial statement of receipt and expenditure of project funds, including co-contributions. Template provided. | 6 November 2026 |
| 13 | Publication | Peer review publications of Fine Scale Suitability Model |  |

### 6.2	Project Metrics

Determine which of the following metrics are relevant to the project and provide a target. Note these metrics can be discussed and agreed with CCIP program director prior to finalisation.

| Tick if applicable | CCIP Metric | Unit of measurement | Target |
| --- | --- | --- | --- |
|  | Number of engagement events with key stakeholders: |  |  |
|  | - Workshops/ meetings with scientific community | Count | 2 |
|  | - Workshops/ meetings with COTS managers | Count | 2 |
|  | - In-field trials/ training with COTS managers | Count | 2 |
|  | Number of new or updated tools developed: |  |  |
|  | - Decision support tools | Count | 1 |
|  | - Models / code / software | Count | 2 |
|  | - Operating procedures / plans | Count | 1 |
|  | - Other: __(list here)_____________ | Count | NA |
|  | Number of external communications: |  |  |
|  | - Scientific papers, reports and publications | Count | 2 |
|  | - Educational tools/ fact sheets etc | Count | NA |
|  | - Media/ social media outputs | Count | NA |
|  | Number Traditional Owners/ First Nations People: |  |  |
|  | - Engaged with by phone, email, online presentation etc | Count | 2 |
|  | - In person engagement (workshops, on Country meetings, field trials etc) | Count | 2 |
|  | - Member of the project team | Count | NA |
|  | - Name groups engaged: __(list here)______________________ |  |  |